# Whisper-based Multi-Accent ASR

Speech-to-Text for an Automobile Diagnostic Center

# 1. Goals

Transcribe conversational audio in Standard, Spanish-accented, and Canadian English.

Output: text + speaker labels + timestamps + punctuation.

Batch / near-real-time (30-60 s lag acceptable).

Self-hosted (privacy-preserving), open source, GPU-backed.

## Non-Goals (v1)

True live captioning (<1 s latency).

Multi-tenant SaaS hardening.

# 2. Architecture

+-------------------- Diagnostic Center Site --------------------+
|  Mic/Headset --> Capture App --> Local WAV (16 kHz mono)       |
|       ^                                                        |
|  Consent + Session Metadata (bay, technician, customer)        |
+----------------------------+-----------------------------------+
                             | HTTPS resumable upload
                             v
+-------------- ASR Backend (self-hosted, GPU) ------------------+
|                                                                |
|  FastAPI Gateway  -->  Redis / RQ Queue                        |
|        ^                       |                               |
|        |                       v                               |
|        |          +------- GPU Worker Pool -------+            |
|        |          | 1. Preprocess (ffmpeg+VAD)   |             |
|        |          | 2. ASR: faster-whisper v3    |             |
|        |          |    + initial_prompt (vocab)  |             |
|        |          | 3. Align: WhisperX wav2vec2  |             |
|        |          | 4. Diarize: pyannote 3.1     |             |
|        |          | 5. Merge speakers + post-fix |             |
|        |          +--------------+---------------+             |
|        |                         v                             |
|        +---- Postgres (transcripts) + S3/MinIO (audio) ----    |
+--------------------------------+-------------------------------+
                                 v
                  Web UI: speaker bubbles, search,
                  click-to-seek, export SRT/JSON/PDF

## Component choices

| Layer | Tech | Why |
| --- | --- | --- |
| Capture | Electron desktop / mobile PWA | Cross-platform mic + consent UI |
| Audio | 16 kHz mono WAV / FLAC | Whisper's native rate |
| Upload | Pre-signed S3 / MinIO PUT | Resumable, decoupled |
| Queue | Redis + RQ (or Celery) | Simple, reliable, GPU-friendly |
| ASR | faster-whisper large-v3 | 4x faster than openai-whisper |
| Alignment | WhisperX (wav2vec2) | Accurate word timestamps |
| VAD | Silero VAD | Removes silence, cleaner diarization |
| Diarization | pyannote.audio 3.1 | SOTA open diarization |
| Storage | Postgres + S3/MinIO | Text vs. blob split |
| API | FastAPI | Async, easy job endpoints |
| Deploy | Docker Compose (v1), K8s later | Start simple |
| GPU | 1x RTX 4090 / cloud L4 | ~$0.40-$1/hr cloud |

# 3. Phased Plan

| # | Phase | Description | Effort |
| --- | --- | --- | --- |
| 0 | GPU + base infra setup | Provision GPU (RTX 4090 / cloud L4), CUDA + Docker + nvidia-container-toolkit, HF token with pyannote license accepted, FastAPI + Postgres + Redis via docker-compose. | 2 days |
| 1 | Whisper ASR core | faster-whisper large-v3 worker, Silero VAD preprocessing, WhisperX forced alignment for word timestamps, /jobs API (submit/status/result), CLI transcribe.py. | 3-4 days |
| 2 | Evaluation harness | Collect ~30 min/accent (Standard, Spanish-accented, Canadian) with consent + ground truth; eval.py computing WER per accent + jargon recall. Acceptance: WER < 15%/accent. | 2-3 days |
| 3 | Automotive domain tuning | Vocabulary list as Whisper initial_prompt (<=224 tokens); regex post-processing (e.g. 'P zero four two zero' -> 'P0420'); optional LLM cleanup pass. | 2-3 days |
| 4 | Diarization (pyannote) | pyannote 3.1 with min/max speakers=2; merge step assigning speaker per word by max-overlap; SPEAKER_00/01 -> Technician/Customer relabel. Acceptance: DER < 15%. | 3-5 days |
| 5 | Capture app + Web UI | Electron/PWA recorder with consent + metadata, resumable upload, web UI with speaker bubbles, click-to-seek, search, export TXT/SRT/JSON/PDF. | ~1 week |
| 6 | Production hardening | OIDC auth, audit logging, at-rest encryption, retention policy, GPU/queue/latency monitoring, backup runbook. | ~1 week |
| 7 | 1-bay pilot | Deploy in one service bay for 2 weeks; daily WER spot-checks; technician feedback loop; iterate vocabulary + relabel UX. | 2 weeks |
| 8 | Extensions (later) | Near-real-time chunked mode (30 s windows), speaker enrollment, topic/intent tagging, auto-draft work-orders via LLM, multilingual (Spanish-only) mode. | later |

# 4. Transcript Data Model

{
  "session_id": "uuid",
  "bay": "Bay-3",
  "technician_id": "T-104",
  "started_at": "2026-05-29T09:14:22Z",
  "duration_sec": 412.7,
  "language": "en",
  "model": "faster-whisper-large-v3",
  "segments": [
    {
      "start": 0.42, "end": 3.18,
      "speaker": "SPEAKER_00",
      "text": "Good morning, what brings you in today?",
      "words": [
        {"w": "Good", "start": 0.42, "end": 0.61, "conf": 0.98},
        {"w": "morning,", "start": 0.62, "end": 0.95, "conf": 0.97}
      ]
    }
  ]
}

# 5. Risk Register

| Risk | Mitigation |
| --- | --- |
| Noisy shop floor (impact wrenches, compressors) | Headset mics; RNNoise/DeepFilterNet preprocessing |
| Heavy accent + jargon -> low WER | Domain initial_prompt; LoRA fine-tune later if needed |
| Diarization confuses overlapping speech | pyannote overlap-aware; force 2 speakers |
| GPU outage | Queue retries; fallback CPU worker for low-priority |
| Privacy / consent | In-app consent; on-prem; encryption; retention policy |
| pyannote commercial license | Free with HF token + acceptance; paid tier for SLA |

# 6. Cost Estimate (1 bay, ~6 hrs audio/day)

| Item | Monthly |
| --- | --- |
| Cloud GPU L4 (8 hrs/day @ $0.50/hr) | ~$120 |
| or on-prem RTX 4090 amortized | ~$50 |
| Storage (Postgres + 200 GB audio) | ~$15 |
| Misc (logging, backups) | ~$10 |
| Total | ~$75-$150 / bay / month |

# 7. Success Metrics

WER <= 10% per accent on eval set

Jargon recall >= 90%

Diarization DER <= 15%

Time-to-transcript <= 1x audio duration on GPU

Technician satisfaction >= 4/5 in pilot survey